## Estimating Available Hours
Sprint 1
Sprint Length |  |  | 1 Week
Workdays during Sprint |  |  | 4 Days
Team Member | Available Days During Sprint | Available Hours per Day | Total Available Hours
Mathias | 3 | 6 | 18
Jacob | 3 | 6 | 18
Jonas | 3 | 6 | 18
Martin | 3 | 6 | 18
Michael | 3 | 6 | 18
Morten | 3 | 6 | 18

## Product Backlog
Product Backlog | Total Sprints: |  | 3 |  | New effort estimate remaining as of sprint
Item | Details | Priority | Business Value Estimate | Effort Estimate | 1 | 2 | 3
DesktopClient |  | 1 |  | 89 | 89 | 34
WebClient |  | 2 |  | 89 | 89 | 21
MyMovieAPI |  | 3 |  | 34 | 34 | 34
Refine Controllers Serverside |  | 4 |  | 34 | 34 | 34
Implement Favourites list |  |  |  | 34 | 34 | 34
RAD: Rework the RAD to comply to new requirements |  | 6 |  | 55 | 55 | 55
SDD :Documentation of subsystem services |  | 7 |  | 5 | 5 | 5
SDD: Global software control |  | 8 |  | 3 | 3 | 3
RAD: Scenario tables |  | 9 |  | 1 | 1 | 1
SDD: Update Class diagrams(Subsystems) |  | 10 |  | 5 | 5 | 5
Draw updated ER diagram for database |  | 11 |  | 2 | 2 | 2
Test Controllers Serverside |  | 12 |  | 8 | 8 | 8
Additional tests for CommunicationFramework |  | 13 |  | 1 | 1 | 1
SDD: Finalize |  | 14 |  | 34 | 34 | 34
Upgrade Web Server Engine Controllers and write general documentation |  | DONE |  | 55 | 55 | 0 | 0
Implement RDBMS module |  | DONE |  | 8 | 8 | 0 | 0
Implement Cache Serverside |  | DONE |  | 34 | 34 | 0 | 0
Backbone: implement StorageSubsystem |  | DONE |  | 89 | 0 | 0 | 0
Backbone: Implement web server engine |  | DONE |  | 89 | 0 | 0 | 0
Investigate how to best implement MVC/MVVM in relation to the two clients |  | DONE |  | 5 | 0 | 0 | 0
Documentation |  | DONE |  | 21 | 0 | 0 | 0
Implement In-memory storage serverside |  | DONE |  | 34 | 34 | 0 | 0
As a user I want to be able to search and find a movie from the title |  | DUBLICATE |  | 34 | 34 | 0
As a user I want to be able to search and find an Actor from the name |  | DUBLICATE |  | 34 | 34 | 0
Backbone: Implement CommunicationSubsystem |  | DONE |  | 55 | 15 | 0
GUI mockup |  |  |  | 2 | 2 | 1
Implement Database |  |  |  | 1 | 1 | 1
As a user I want to be able to make and view my favourites list |  |  |  | 34 | 34 | 34
As an Administrator I want to be able to add, edit and delete information in the database |  |  |  | 55 | 55 | 34
As a user or administrator I want to be able to log into my account |  |  |  | 21 | 21 | 21
As a user I want to be able to register a new account |  |  |  | 13 | 13 | 13
As a user I want to be able to remove movies from my favourites list |  |  |  | 5 | 5 | 5
Update requirements to include requirement for .NET 4.5+ |  |  |  | 1 | 1 | 1
Users |  |  |  | 55 | 55 | 55
Ideal Remaining Hours |  |  |  | 1039 | 692.6667 | 346.3333 | 0
Actual Remaining Hours |  |  |  | 1039 | 795 | 436
Release burndown chart

## Sprint 1
Sprint 1 | Total days: | 3 |  | New estimates of effort remaining as of day
Product Backlog Item | Sprint Task | Volunteer | Initial Estimate of Effort | 1 | 2 | 3
Backbone: Implement StorageSubsystem | Investigate how to implement database | Martin | 2 | 0 | 0 | 0
| Implement Database | Jacob | 8 | 1 | 1 | 1
| Implement RDBMS module | Jacob & Michael | 34 | 34 | 13 | 8
| Implement StorageSubsystem | Jacob & Michael | 34 | 34 | 21 | 0
Documentation | SDD: Hardware/software mapping | Jacob | 2 | 2 | 2 | 0
| SDD: Global software control | Morten | 3 | 3 | 3 | 3
| RAD: Scenario tables | Morten | 1 | 1 | 1 | 1
Backbone: Implement Web Server Engine | Design facade interface | Morten & Jonas | 13 | 2 | 2 | 2
| Design DTO interfaces | Morten & Jonas | 5 | 1 | 1 | 0
| Implement | Morten & Jonas | 55 | 55 | 21 | 5
Backbone: Implement ServerCommunicationSubsystem | Research how to implement a framework | Mathias & Martin | 3 | 0 | 0 | 0
| Implement ServerSocket | Mathias & Martin | 34 | 34 | 13 | 13
| Implement HTTPListener | Mathias & Martin | 21 | 21 | 13 | 2
Investigate how to best implement MVC/MVVM in relation to the two clients | Investigate | Jonas | 8 | 5 | 5 | 0
Ideal Remaining Hours |  |  | 223 | 148.6667 | 74.3333 | 0
Actual Remaining Hours |  |  | 223 | 193 | 96 | 35

## Sprint 2
Sprint 2 | Total days: | 7 |  | New estimates of effort remaining as of day
Product Backlog Item | Sprint Task | Volunteer | Initial Estimate of Effort | 1 | 2 | 3 | 4 | 5 | 6 | 7
Upgrade Web Server Engine Controllers and write general documentation | Implement Search Controller | Jonas | 8 | 5 | 3 | 3 | 0 | 0 | 0 | 0
| Implement | Jonas | 55 | 34 | 13 | 0 | 0 | 0 | 0 | 0
| Documentation | Jonas | 13 | 13 | 13 | 8 | 3 | 3 | 3 | 3
Implement RDBMS module | Testing & Documentation | Jacob | 8 | 8 | 8 | 1 | 1 | 1 | 1 | 1
Backbone: Implement ServerCommunicationSubsystem | WebServer Class implementation | Martin | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0
GUI mockup | mockup | Mathias, Morten & Michael | 2 | bar: New estimates of effort remaining as of day 1 to New estimates of effort remaining as of day 7
Implement Cache Serverside | Implement | Jacob | 34 | 34 | 3 | 0 | 0 | 0 | 0 | 0
MyMovieAPI | Implement | Jacob | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34
DesktopClient | Implement logic | Mathias | 68 | 68 | 55 | 34 | 34 | 21 | 21 | 21
| Implement XAML | Mathias | 21 | 21 | 21 | 13 | 5 | 5 | 5 | 5
Implement Database | Documentation | Jacob | 1 | bar: New estimates of effort remaining as of day 1 to New estimates of effort remaining as of day 7
Implement in-memory database | Implement | Jacob | 34 | 34 | 34 | 34 | 21 | 0 | 0 | 0
WebClient | Web GUI | Michael | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0
| Implement logic | Martin | 60 | 60 | 60 | 55 | 55 | 34 | 34 | 21
| Research MVC | Martin & Michael | 21 | 13 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Remaining work |  |  | 369 | 316.2857 | 263.5714 | 210.8571 | 158.1429 | 105.4286 | 52.7143 | 0
Actual Remaining work |  |  | 369 | 336 | 255 | 193 | 163 | 100 | 100 | 87

## Sprint 3
Sprint 2 | Total days: | 6 |  | New estimates of effort remaining as of day
Product Backlog Item | Sprint Task | Volunteer | Initial Estimate of Effort | 1 | 2 | 3 | 4 | 5 | 6
DesktopClient | Finalize DesktopClient | Mathias | 34 | New estimates of effort remaining as of day 1: 34; New estimates of effort remaining as of day 2: 21; New estimates of effort remaining as of day 3: 13
WebClient | GUI | Jacob | 34 | New estimates of effort remaining as of day 1: 34; New estimates of effort remaining as of day 2: 21; New estimates of effort remaining as of day 3: 21
| Finalize WebClient Logic | Martin | 21 | 13 | 5 | 0 | 0 | 0 | 0
MyMovieAPI | Implement MyMovieAPI | Jacob | 34 | 21 | 2 | 2 | 2 | 2 | 2
Refine Controllers Serverside | Additional tests | Jonas | 4 | 0 | 0 | 0 | 0 | 0 | 0
| Refine | Jonas | 30 | 13 | 2 | 0 | 0 | 0 | 0
RAD: Rework the RAD to comply to new requirements | Update functional and non-functional requirements | Michael | 3 | 3 | 0 | 0 | 0 | 0 | 0
| Update usecases and usecase diagram | Morten | 13 | 13 | 0 | 0 | 0 | 0 | 0
| Update scenarios | Morten | 5 | 5 | 0 | 0 | 0 | 0 | 0
| Finalize RAD | ALL | 34 | New estimates of effort remaining as of day 1: 34; New estimates of effort remaining as of day 2: 34; New estimates of effort remaining as of day 3: 34
SDD | Global access control and security | Morten | 5 | New estimates of effort remaining as of day 1: 5; New estimates of effort remaining as of day 2: 5; New estimates of effort remaining as of day 3: 5
| Update subsystem decomposition | Morten | 21 | New estimates of effort remaining as of day 1: 21; New estimates of effort remaining as of day 2: 13; New estimates of effort remaining as of day 3: 8
| Update Subsystem(component) services | Michael | 8 | 8 | 8 | 0 | 0 | 0 | 0
| Finalize SDD | ALL | 34 | New estimates of effort remaining as of day 1: 34; New estimates of effort remaining as of day 2: 34; New estimates of effort remaining as of day 3: 34
Draw updated ER diagram for database | Draw ER diagram | Jacob | 2 | 2 | 2 | 0 | 0 | 0 | 0
Integration Testing | Research how to best do it | Jonas | 3 | 3 | 3 | 0 | 0 | 0 | 0
| Do integration testing | Jonas | 13 | New estimates of effort remaining as of day 1: 13; New estimates of effort remaining as of day 2: 13; New estimates of effort remaining as of day 3: 8
Additional tests for CommunicationFramework | Additional tests for CommunicationFramework | Martin | 1 | bar: New estimates of effort remaining as of day 1 to New estimates of effort remaining as of day 3
Ideal Remaining work |  |  | 231 | 192.5 | 154 | 115.5 | 77 | 38.5 | 0
Actual Remaining work |  |  | 231 | New estimates of effort remaining as of day 1: 257; New estimates of effort remaining as of day 2: 164; New estimates of effort remaining as of day 3: 126

## Velocity
Sprint nr. | Velocity
Sprint 1 | 188
Sprint 2 | 282
Sprint 3
Average | 235