## Sheet1
Sprint 1 | Total days: | 3 |  | New estimates of effort remaining as of day
Product Backlog Item | Sprint Task | Volunteer | Initial Estimate of Effort | 1 | 2 | 3
As a user I want register and log in | User database | Mathias | 4 | 3 | 1 | 0
| Registration | Jonas | 4 | 3 | 0 | 0
| Loging | Morten | 4 | 3 | 1 | 0
Ideal Remaining Hours |  |  | 12 | 8 | 4 | 0
Actual Remaining Hours |  |  | 12 | 9 | 2 | 0